## Blad1
Data |  | Maxim | Kwinten
1. | date | 2022-10-11
| # hours | 1 hour
| description | Chosen front end & back end framework + database. (VueJS & NodeJS + MongoDB) Setup the project with necessary files.
2. | date | 2022-10-20
| # hours | 2 hours
| description | Created Login and SignUp components in VueJS.
3. | date | 2022-10-25
| # hours | 1 hour
| description | Created presentation for the intermediary presentation.
4. | date | 2022-11-05
| # hours | 1,5 hours
| description | Setup the database and connected it to the application with Mongoose. (+ created necessary schemas)
5. | date | 2022-11-16
| # hours | 2 hours
| description | Made users able to sign up and log in (=> store users in database)
6. | date | 2022-11-20
| # hours | 1,5 hours
| description | Provided front side form validation + server side form validation.
7. | date | 2022-12-01
| aantal uren | 2 hours
| beschrijving | Created Home Page for new users. (= entry page for website) + footer
8. | date | 2022-12-05
| # hours | 1,5 hours
| description | Added search bar on Organiser side to search for companies + backend. (asynchronous requests to server)
9. | date | 2022-12-10
| # hours | 1,5 hours
| description | Added profile page for users to see their user data. (display data from the database in form fields)
10. | date | 2022-12-11
| # hours | 2 hours
| description | Make it available for users to update their profile data except for the password.
11. | date | 2022-12-12
| # hours | 0,5 hour
| description | Make it available for users to log out from their accounts.
11. | date | 2022-12-13
| # hours | 2 hours
| description | Adding Leaflet map component + indicating current location on the map + indicating nearby companies on the map.